## Sheet1
PROJECT NUMBER | 26
PROJECT NAME | Resolve App
PROJECT MENTOR (sponsor) | Sai KUmar Reddy
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | ALL | 1 | 0.5 | Done |  | 0.5 | 50
GIT Repository setup | Preparation | ALL | 1 | 1.5 | Done | initial setup is ready and all team members are added to it | -0.5 | 50
Client meeting | Coordination | ALL | 5 | 1 | Done | discuss about project idea and how to start project | 4 | 80
Get account and configure website | Preparation | ALL | 1.5 | 1 | Done |  | -0.5 | 33.33
Research existing technology | Preparation | ALL | 2 | 2 | Done |  | 0 | 0
Project synopsis writeup | Documentation | Neel and kevin | 2 | 1.5 | Done | completed the document as provided by the Prof., filling all the details | 0.5 | 25
Identify role owners | Preparation | ALL | 0.5 | 0.5 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0 | 0
Team Meeting | Coordination | ALL | 1 | 2 | Done | meeting on a regular basis to discuss ideas | -1 | 50
Status tracker | Documentation | Gopendra and Sujal | 1 | 0.75 | Done | updating the excel sheet on a weekly basis | 0.25
Week 2 (January 22 - January 28)
Designing of UI | Preparation | ALL | 4 |  | Running
Client meeting | Coordination | ALL | 1 | 0.75 | Done |  | 0.25 | 25
Develop questions for requirements elicitation | Documentation | ALL | 3 | 1.5 | Done | all question must included for all requirement | 1.5 | 50
Get account and configure website | Preparation | ALL | 1.5 |  | Running
Team Meeting | Coordination | ALL | 1 | 0.5 | Done |  | 0.5 | 50
Status tracker | Documentation | ALL | 1 | 0.75 | Done | to be completed after 28th january | 0.25 | 25
Research existing technology | Preparation | ALL | 1 | 0.75 | Done | for frontend and backend part | 0.25 | 25
Week 3 (January 29 - February 4)
Designing of UI | Preparation | Neel and kevin | 4 |  | Running | Started designing UI
Client meeting | Coordination | ALL | 1 |  | Done
Exploring Competitors | Preparation | ALL | 2 | 2.5 | Done |  | -0.5 | 25
Creating Prototype and basic design in Figma | Preparation | Gopendra and Sujal | 3 |  | Running | Collaborated through brainstorming section in figma and created design for web pages
Team Meeting | Coordination | ALL | 1 | 1.5 | Done |  | -0.5 | 50
Refining Requirements | Documentation | ALL | 1.5 | 1 | Done |  | -0.5 | 33
Week 4 (February 5 - February 11)
Designing of UI | Preparation | ALL | 4 |  | Running
Client meeting | Coordination | ALL | 1 |  | Done | Client was going to visit campus and have physical meet but it got cancelled
Learning React, Express | Preparation | ALL | 2 |  | Running | Also had tutorial session on it
Learning Node js | Preparation | ALL | 2 |  | Running | Also had tutorial session on it
Team Meeting | Coordination | ALL | 1 | 1 | Done |  | 0 | 0
Creating Prototype and basic design in Figma | Preparation | ALL | 3 | 4 | Done |  | -1 | 33
Week 5 (February 12 - February 18)
Designing of UI | Preparation | ALL |  |  | Running
Client meeting 1 | Coordination | ALL | 1 | 0.5 | Done |  | 0.5 | 50
Learning React, Express | Preparation | ALL |  |  | Running
Learning Node js | Preparation | ALL |  |  | Running
Team Meeting | Coordination | ALL | 1 | 1.5 | Done | Discussion on MoMs and design and flow of pages. | -0.5 | 50
Client meeting 2 | Coordination | ALL | 0.5 | 0.75 | Done | Discussed on SRS and presented implemented pages. | -0.25 | 50
Login page and User Authentication | Preparation | Neel and kevin | 8 | 9 | Done | Frontend implementation done. | -1 | 12.5
SRS Document | Documentation | Gopendra and Sujal | 5 | 7 | Done | Came up with doubts and had discusion on it with client | -2 | 40
Week 6 (February 19 - February 25)
Designing of dashboard | Preparation | ALL |  |  | Running
Learning React, Express | Preparation | ALL |  |  | Running
Learning Node js | Preparation | ALL |  |  | Running
Client meeting | Coordination | ALL | 1 | 0.5 | Done | Had a short meet with client to discuss on srs doubts | 0.5 | 50
Team Meeting | Coordination | ALL | 1 | 0.75 | Done |  | 0.25 | 25
Week 7(February 26 – March 3)
Designing of dashboard | Preparation | ALL |  |  | Running
Learning React, Express | Preparation | ALL |  |  | Running
Learning Node js | Preparation | ALL |  |  | Running
Client meeting | Coordination | ALL |  |  | Done
Team Meeting | Coordination | ALL | 1 | 0.5 | Done | After midsem, decided the future tasks and deadlines for it. | 0.5 | 50
Week 8(March 4 – March 10)
Designing of dashboard | Preparation | ALL | 5 | 7 | Done |  | -2 | 40
Learning React, Express | Preparation | ALL |  |  | Running
Learning Node js | Preparation | ALL |  |  | Running
Client meeting 1 | Coordination | ALL | 1 | 0.5 | Done | Work display | 0.5 | 50
Team Meeting | Coordination | ALL | 1 | 1.5 | Done | Decided flow of pages | -0.5 | 50
Sign up/Sign in authentication | Implementation | Gopendra and Sujal | 4 | 5 | Done |  | -1 | 25
Landing and dashboard UI | Implementation | Neel and kevin | 5 | 5.5 | Done |  | -0.5 | 10
Firebase integration | Implementation | Gopendra and Sujal | 4 | 3 | Done |  | 1 | 25
Complaint form and data charts | Implementation | Neel and kevin | 2 | 3 | Done |  | -1 | 50
Client meeting 2 | Coordination | ALL | 1 | 1 | Done | Brainstorming session and work display | 0 | 0
Week 9(March 11 – March 17)
Team Meeting 1 | Coordination | ALL | 1 | 1.5 | Done | Decided analytics part | -0.5 | 50
Learning React | Preparation | ALL |  |  | Running
Learning Firebase | Preparation | ALL |  |  | Running
Adding analytics in dashboard | Implementation | Gopendra and Kevin | 4 | 7 | Done |  | -2 | 50
File complaint and assigning admin | Implementation | Neel | 6 | 8 | Done |  | -2 | 33.33
Session management | Implementation | Sujal | 5 | 6 | Done |  | -1 | 20
Integration of dashboard, authentication and complaint forms | Implementation | ALL | 3 | 5 | Done |  | -2 | 66.66
Team Meeting 2 | Coordination | ALL | 1 | 0.75 | Done | Discussed testing and presentation | 0.25 | 25
Week 10(March 18 – March 24)
Team Meeting | Coordination | ALL | 1 | 1.5 | Done |  | -0.5 | 50
Client meeting | Coordination | ALL |  |  | Cancelled | not happen
Learning Firebase | Preparation | ALL |  |  | Running
Learning React | Preparation | ALL |  |  | Running
Week 11(March 25 – March 31)
Client meeting | Coordination | ALL | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | ALL | 0.5 | 1 | Done | discussed about r1 feedback and plan for r2 | -0.5 | 50
Learning Firebase | Preparation | ALL |  |  | Running
Learning React | Preparation | ALL |  |  | Running
Messaging api | Preparation | Neel and kevin |  |  | Running
Notification alert | Preparation | Gopendra and Sujal |  |  | Running
Week 12(April 1 – April 7)
Team Meeting | Coordination | ALL | 0.5 | 1 | Done |  | -0.5 | 50
Client meeting | Coordination | ALL |  |  | Cancelled | client did not responded
Learning Firebase | Preparation | ALL |  |  | Running
Learning React | Preparation | ALL |  |  | Running
Messaging api | Preparation | Neel and kevin |  |  | Running
Notification alert | Preparation | Gopendra and Sujal |  |  | Running
Week 13(April 8 – April 14)
Team Meeting | Coordination | ALL | 1 | 0.5 | Done |  | 0.5 | 50
Client meeting | Coordination | ALL | 0.5 | 0.5 | Done |  | 0 | 0
Learning Firebase | Preparation | ALL |  |  | Running
Learning React | Preparation | ALL |  |  | Running
Messaging api | Preparation | Neel and kevin | 6 | 8 | Done |  | -2 | 33.33
Notification alert | Preparation | Gopendra and Sujal | 5 | 6 | Done |  | -1 | 20
Analytics and graphs | Preparation | Gopendra and Sujal |  |  | Running
integration testing | Preparation | ALL |  |  | Running
Responsive form | Preparation | Neel and kevin |  |  | Running
Week 14(April 15 – April 21)
Team Meeting | Coordination | ALL | 1 | 3 | Done |  | -2 | 200
Client meeting | Coordination | ALL | 2 | 1.5 | Done | gave website demo to the client | 0.5 | 25
Analytics and graphs | Preparation | Gopendra and Sujal | 4 | 5 | Done |  | -1 | 25
integration testing | Preparation | ALL | 2 | 3 | Done |  | -1 | 50
Responsive form | Preparation | Neel and kevin | 1 | 1.5 | Done |  | -0.5 | 50
Learning Firebase | Preparation | ALL |  |  | Running
Learning React | Preparation | ALL |  |  | Running
system testing | Preparation | ALL | 2 | 4 | Done |  | -2 | 100